## Info
Defect Report for Project
Project Name | VWO Application – Authentication Module
Prepared by | Nagashree
Prepared on | 2023-08-08
Field | Explanation
Defect ID | A unique identifier given to each bug or defect to track it easily in the defect management tool (e.g., BUG_001 ).
Defect Title | A short, clear summary of the defect. It should explain what the issue is in 1 sentence (e.g., Login fails with valid credentials ).
Reported By | The name of the tester or team member who discovered and reported the defect.
Reported On | The date when the defect was reported. This helps in tracking the age of the bug.
Environment | The system configuration where the bug occurred. Includes: platform (Web/Mobile), browser (e.g., Chrome v114), and OS (e.g., Windows 10). It’s useful for reproducing the issue.
Module | The specific section or page of the application where the bug was found (e.g., Login Page , Checkout Page ).
Severity | Indicates the impact level of the defect on the system:
Priority | Defines how urgent it is to fix the defect. Set by QA team or product owner.
Steps to Reproduce | This field describes the exact sequence of actions a tester took to discover the defect. It helps the developer replicate the issue in their own environment.
Expected Result | The "Expected Result" field describes what the application should do under normal, correct conditions—based on requirements, user stories, or design documents.
Actual Result | The "Actual Result" field describes what the application actually did when the test was performed—even if that behavior was incorrect.
Attachments | The "Attachments" field is used to provide supporting evidence of the defect—such as screenshots, screen recordings (videos), log files, or console errors.
Defect Status | The "Defect Status" field shows the current stage of a defect in its life cycle—from the moment it is reported until it is resolved or closed.
Assigned To | The "Assigned To" field indicates the name of the developer (or responsible team member) who is currently assigned to investigate and fix the defect.
Retested By | The "Retested By" field captures the name of the QA tester who verified the defect fix after the developer marked it as “Fixed.”
Retest Date | The "Retest Date" field records the date on which the tester re-verified the defect after the developer marked it as “Fixed.”
Resolution | The "Resolution" field describes the final outcome or decision taken regarding the defect after it has been reviewed, worked on, or closed.
Comments | The "Resolution" field describes the final outcome or decision taken regarding the defect after it has been reviewed, worked on, or closed.

## VWO_Auth_Bug_Sheet
Defect ID | Defect Title | Module | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Attachments | Reported By | Reported On | Environment | Defect Status | Assigned To | Retested By | Retest Date | Resolution | Comments